## Sheet1
Task | Start | End | Duration | % Complete | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Cover Page
Contents page
Proposal | Week 1 | Week 3 | 3 weeks | bar: Week 1 to Week 3
Planning
Initial ideas, thought processes and research into themes | Week 1 | Week 4 | 4 weeks | 100 | bar: Week 1 to Week 4
Crirical review and analysis of other work | Week 2 | Week 4 | 3 weeks | 100 | bar: Week 2 to Week 4
Important research information - include URLs | Week 1 | Week 4 | 4 weeks | 100 | bar: Week 1 to Week 4
Schedule with specific time objectives | Week 2 | Week 5 | 4 weeks | 100 | bar: Week 2 to Week 5
Any copies of correspondance relating to the project | Week 3 | Week 5 | 3 weeks | 50 | bar: Week 3 to Week 5
Description of treatment and concept | Week 3 | Week 5 | 3 weeks | bar: Week 3 to Week 5
Asset lists, storyboards, scripts, design skethes | Week 3 | Week 6 | 4 weeks | bar: Week 3 to Week 6
Architecture flow diagrams | Week 3 | Week 6 | 4 weeks | bar: Week 3 to Week 6
Evaluations and critical thought | Week 3 | Week 6 | 4 weeks | bar: Week 3 to Week 6
Audience
Target audience, marketing and promotion | Week 5 | Week 7 | 3 weeks | bar: Week 5 to Week 7
Include examples from other works | Week 5 | Week 7 | 3 weeks | bar: Week 5 to Week 7
A brief pitch of your idea to sell your idea to someone | Week 5 | Week 7 | 3 weeks | bar: Week 5 to Week 7
Budget | Week 5 | Week 7 | 3 weeks | bar: Week 5 to Week 7
Development
Prototypes | Week 6 | Week 8 | 3 weeks | bar: Week 6 to Week 8
Experiment | Week 6 | Week 8 | 3 weeks | bar: Week 6 to Week 8
Segments of completed work and designs | Week 6 | Week 8 | 3 weeks | bar: Week 6 to Week 8
Designs beyond sketch and planning stage | Week 6 | Week 8 | 3 weeks | bar: Week 6 to Week 8
Supply links to blogs | Week 6 | Week 8 | 3 weeks | bar: Week 6 to Week 8
Describe what is left todevelop for the project | Week 6 | Week 8 | 3 weeks | bar: Week 6 to Week 8
Statement of whether you are on target | Week 6 | Week 8 | 3 weeks | bar: Week 6 to Week 8
Personal reflection
Prototype to be tested by users, preferably by the target audience | Week 8 | Week 12 | 5 weeks | bar: Week 8 to Week 12
Collect and analyse feedback | Week 8 | Week 12 | 5 weeks | bar: Week 8 to Week 12
Reflect on feedback collected to make improvements to the project | Week 8 | Week 12 | 5 weeks | bar: Week 8 to Week 12
Personal reflection 500 words | Week 8 | Week 12 | 5 weeks | bar: Week 8 to Week 12
Critical Evaluation 500 words | Week 8 | Week 12 | 5 weeks | bar: Week 8 to Week 12